## Slide 1: Project Scheduling and Tracking
CIS 375
Bruce R. Maxim
UM-Dearborn

## Slide 2: Planning Objectives
To provide a framework that allows a software manager to make an estimate of resources, cost, and schedule.
Project outcomes should be bounded by 'best case' and 'worst case' scenarios.
Estimates should be updated as the project progresses.

## Slide 3: Scope Definition
Determine the customer's overall goals for the proposed system and any expected benefits.
Determine the customer's perceptions concerning the nature of a good solution to the problem.
Evaluate the effectiveness of the customer meeting.

## Slide 4: Product Feasibility
Technical feasibility is not a good enough reason to build a product.
The product must meet the customer's needs and not be available as an off-the-shelf purchase.

## Slide 5: What does the customer want to know?
Do you understand my needs?
Can you design a system to help me?
How long will it take?
How much will it cost?

## Slide 6: People and Effort
Adding people to a project after it is behind schedule often causes the schedule to slip further
The relationship between the number of people on a project and overall productivity is not linear (e.g. 3 people do not produce 3 times the work of 1 person, if the people have to work in cooperation with one another)
The main reasons for using more than 1 person on a project are to get the job done more rapidly and to improve software quality.

## Slide 7: Productivity and People

## Slide 8: Matching People to Tasks (Myer-Briggs)

## Slide 9: Software Team Organization
Democratic decentralized
  rotating task coordinators
  group consensus
Controlled decentralized
  permanent leader
  group problem solving
  subgroup implementation of solutions
Controlled centralized
  top level problem solving
  internal coordination managed by team leader

## Slide 10: Chief Programmer Team

## Slide 11: Democratic

## Slide 12: Factors Affecting Team Organization
Difficulty of problem to be solved
Size of resulting program
Team lifetime
Degree to which problem can be modularized
Required quality and reliability of the system to be built
Rigidity of the delivery date
Degree of communication required for the project

## Slide 13: Process
Framework activities populated with
Tasks milestones
Work products
Quality Assurance points

## Slide 14: Framework Activities
Customer communication
Planning
Risk analysis
Engineering
Construction and release
Customer evaluation

## Slide 15: Process Considerations - 1
Process model chosen must be appropriate for the:
  customers
  developers
  characteristics of the product
  project development environment
Project planning begins with melding the product and the process

## Slide 16: Process Considerations - 2
Each function to be engineered must pass though the set of framework activities defined for a software organization
Work tasks may vary but the common process framework (CPF) is invariant (e.g. size does not matter)
Software engineer’s task is to estimate the resources required to move each function though the framework activities to produce each work product

## Slide 17: Managing the Project
Start on the right foot
Maintain momentum
Track progress
Make smart decisions
Conduct a postmortem analysis

## Slide 18: Critical Practices
Formal risk management
Empirical cost and schedule estimation
Metric-based project management
Earned value tracking
Defect tracking against quality targets
People-aware program management

## Slide 19: Scheduling Principles - 1
Compartmentalization
  the product and process must be decomposed into a manageable number of activities and tasks
Interdependency
  tasks that can be completed in parallel must be separated from those that must completed serially
Time allocation
  every task has start and completion dates that take the task interdependencies into account

## Slide 20: Scheduling Principles - 2
Effort validation
  project manager must ensure that on any given day there are enough staff members assigned to completed the tasks within the time estimated in the project plan
Defined Responsibilities
  every scheduled task needs to be assigned to a specific team member

## Slide 21: Scheduling Principles - 3
Defined outcomes
  every task in the schedule needs to have a defined outcome (usually a work product or deliverable)
Defined milestones
  a milestone is accomplished when one or more work products from an engineering task have passed quality review

## Slide 22: Step 1 List the Deliverables
Documents.
Demonstration of function.
Demonstration of subsystem.
Demonstration of accuracy.
Demonstration of reliability, security, or speed.

## Slide 23: Step 2 Define the Milestones
Completion of an activity or deliverable (must be measurable).
Activities must have definite a start and stop.
A milestone is point in time not a time period like an activity.

## Slide 24: Step 3 Work Breakdown Structure
Create the work breakdown structure (task network)
Separate the project into phases composed of steps
Subdivide steps into activities as needed

## Slide 25: Project Effort Distribution
Generally accepted guidelines are:
  02-03 % planning
  10-25 % requirements analysis
  20-25 % design
  15-20 % coding
  30-40 % testing and debugging

## Slide 26: Defining a Task Set
Consider project type.
Degree of rigor.
Review rigor adaptation criteria.
Determine task selector value.
Consider concept development tasks.

## Slide 27: Software Project Types - 1
Concept development
  initiated to explore new business concept or new application of technology
New application development
  new product requested by customer
Application enhancement
  major modifications to function, performance, or interfaces (observable to user)

## Slide 28: Software Project Types - 2
Application maintenance
  correcting, adapting, or extending existing software (not immediately obvious to user)
Reengineering
  rebuilding all (or part) of a legacy system

## Slide 29: Software Process Degree of Rigor - 1
Casual
  all framework activities applied, only minimum task set required (umbrella activities minimized and documentation reduced)
Structured
  all framework and umbrella activities applied (SQA, SCM, documentation, and measurement tasks are streamlined)

## Slide 30: Software Process Degree of Rigor - 2
Strict
  full process and umbrella activities applied (high quality products and robust documentation produced)
Quick reaction
  emergency situation, process framework used, but only tasks essential to good quality are applied (back filling used to develop documentation and conduct additional reviews after product is delivered)

## Slide 31: Rigor Adaptation Criteria
Size of project
Number of potential users
Mission criticality
Application longevity
Requirement stability
Ease of customer/developer communication
Maturity of applicable technology
Performance constraints
Embedded/non-embedded characteristics
Project staffing
Reengineering factors

## Slide 32: Activity Graph
Each activity has:
Precursor
Duration
Due date
End point (milestone or deliverable)

## Slide 33: CPM Critical Path Method
http://groups.umd.umich.edu/cis/tinytools/cis375/f00/cpm/CPM(1).HTM

## Slide 34
Activity
Precursor
Duration
EST
EFT
LST
LFT
Slack
Start
-
0
0
0
0
0
0
A
Start
2
0
2
0
2
0
B
Start
3
0
3
4
7
4
C
A
5
2
7
2
7
0
D
A,B
4
3
7
7
11
4
E
D
2
7
9
11
13
4
F
B,C
6
7
13
7
13
0
FINISH
E,F
0
13
13
13
13
0
EST = earliest start time, EFT = earliest finish time.
LST = latest start time, LFT = latest finish time.
Slack = (LST - EST) or (LFT - EFT).

## Slide 35: CPM Equations
EST(START) always = 0, EFT(START) always = 0.
LST(START) always = 0, LFT(START) always = 0.
EFT(I) = EST(I) + DUR(I).
EST(I) = max(EFT of all predecessors).
LST(I) = LFT(I) - DUR(I).
LFT(I) = min(LST of all sucessors).
LFT(FINISH) = LST(FINISH) = EST(FINISH) = EFT(FINISH).
Critical path is all nodes with Slack = 0.

## Slide 36: Program Evaluation and Review Technique
JAN
FEB
TASK
EARLIEST START
LATEST START
1
8
15
22
29
5
12
17
24
1
1/1
2/5
*
*
*
*
*
*
2
1/1
1/8
*
*
3
1/9
1/22
*
*
*
*
4
1/9
1/22
*
*
*
*
5
1/23
2/1
*
*
*
6
1/23
2/1
-
-
F
7
1/23
2/17
-
-
F
F
F
8
2/2
2/17
*
*
*
*
* = critical activity, - = non-critical, F = float or slack

## Slide 37: Gantt Chart

## Slide 38: Overlay Resources on Gantt Chart

## Slide 39: Milestone Chart

## Slide 40: Line Graph

## Slide 41: Earned Value Analysis
Earned value is a quantitative measure of percent of project completed so far.
The total hours to complete the entire project are estimated and each task is given an earned value based on its estimated percentage contribution to the total.
http://groups.umd.umich.edu/cis/course.des/cis525/js/f00/tejal/form.htm

## Slide 42: Error Tracking
Allows comparison of current work to past projects and provides a quantitative indication of the quality of the work being conducted.
The more quantitative the approach to project tracking and control, the more likely problems can be anticipated and dealt with in a proactive manner.