CIS 375 SOFTWARE ENGINEERING

University Of Michigan-Dearborn

Dr. Bruce Maxim, Instructor

Management & Object Oriented Projects:

- Establish a common process framework (CPF).

- Use CPF & historic data to eliminate time & effort.

- Specify products & milestone.

- Define Q.A. checkpoints.

- Manage changes.

- Monitor.

- Project Metrics:

- Number of scenario scripts.

- Number of key classes.

- Number of support classes.

- (# of key classes)/(# of support classes).

Object Oriented Estimating & Scheduling:

- Develop estimates using effort decomposition, FP, etc.

- Use O.O.A. to develop scenario script and count them.

- Use O.O.A. to get the number of key classes.

- Categorize types of interfaces:

- No U.I. = 2.0		G.U.I. = 3.0

- Text U.I. = 2.25	Complex G.U.I. = 3.0

- Use to derive support classes:

- (# of key classes) * (G.U.I. #)

- Total classes = (key + support) * (average # of work units per class).

- ( 15-20 person days per class)

- Cross check class based estimate (5) by multiplying.

- (avg. # of work units) * (# of scenario scripts)

Project Scheduling Metrics:

- Number of major iterations (around spiral model).

- Number if completed contracts.

(Goal: at least 1 per iteration)

Object Oriented Milestones:

- Contracts completed.

- O.O.A. completed.

- O.O.D. completed.

- O.O.P. completed.

- O.O. testing completed.