CIS 375 SOFTWARE ENGINEERING

University Of Michigan-Dearborn

Dr. Bruce Maxim, Instructor

Cost Estimation:

Types Of Costs:

- Facilities.

- People.

- Project methods and tools.

Types Of Cost Models:

- Experiential (derived from past experience).

- Static (similar to regression, doesn’t change with time).

- Dynamic (often includes the effects of time).

Expert Judgment (experienced guessing):

A = The most pessimistic estimate.

B = The most likely estimate.

C = The most optimistic estimate.

(A + 4B + C)

Ê =       6

(Weighted average; where Ê = estimate).

Delphi Technique:

- A group of experts, make “secret” guesses.

- These “secret” guesses are used to obtain a group average.

- The group average is presented to the group.

- The group, once again makes “secret” guesses.

- Individual guesses are again averaged.

- If new average is different from previous, then goto (4).

- Else Ê = new average.

Wolverton Model:

(Uses a software type matrix):

{old, new}  {easy, moderate, hard}.

Estimate models in terms of: lines of code.

C(k)            =            S(k)         -       Ci,j(k)

Cost of module k = Size of module k - Value from matrix.

System =  C(k).

Function Points:

(Not dependent on estimating lines of code).

| Parameter | Simple | + | Average | + | Complex | = | Fi |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Distinct input items | 3( ) | + | 4( ) | + | 6( ) | = | ? |
| Output screens/reports | 4( ) | + | 5( ) | + | 7( ) | = | ? |
| Types of user queries | 3( ) | + | 4( ) | + | 6( ) | = | ? |
| Number of files | 7( ) | + | 10( ) | + | 15( ) | = | ? |
| External interface | 5( ) | + | 7( ) | + | 10( ) | = | ? |
|  |  |  |  |  | Total | = | ? |

# of F.P.’s =  T(total)  ([0.65 + 0.01](empirical constants)  Q)

{Q = score from questionnaire}

Function Point Questionnaire:

(importance of {0-5; 0 = minimal & 5 = essential})

- Backup.

- Data communication.

- Distributed processes.

- Optimal performance.

- Heavily used operating system.

- On-line data security.

- Multiple screens.

- On-line master file update.

- Complex inputs, queries, outputs.

- Complex internal processing.

- Reusable code.

- Conversion or installation.

- Multiple user sites.

- Ease of use.

Cost of producing one function point?  May be organization specific.

Problems With Expert Judgment:

- It is subjective. (consensus is difficult to achieve)

- Extrapolating from one project to another may be difficult.

- Users and project managers tend not to estimate costs very well.

- Cost matrices require periodic updates.