CIS 375 SOFTWARE ENGINEERING

University Of Michigan-Dearborn

Dr. Bruce Maxim, Instructor

Risks Analysis:

- Risk identification.

- Risk projection (impact of risks/likelihood of risk actually happening).

- Risk assessment (the change if it happens).

- Risk management.

Kinds Of Risk:

- Project risks:

- Schedule, budget, people, resources, etc.

- Technical risks:

- Design, implementation, interfacing, etc.

- Business risks:

- Building a project that the public actually wants.

Risk Projection (or estimation):

- Likelihood that a risk is real.

- Consequences of problem, if it occurs.

Risk Planner:

- Establish a scale indicating perceived likelihood.

- Determine consequences.

- Estimate impact on project (for each risk).

- Note overall accuracy of risk projection (to avoid misunderstanding).

Date: 9/24/97

Week 3

Sample Impact Assessment Table:

| CATEGORY \ COMPONENTS |  | PERFORMANCE | SUPPORT | COST | SCHEDULE |
| --- | --- | --- | --- | --- | --- |
|  | 1 | Failure to meet would result in mission failure |  | Failure results in increased costs and schedule delays with expected values in excess of $500K |  |
| CATASTROPHIC | 2 | Significant degradation to nonachievement of technical performance | Nonresponsive or unsupportable software | Significant, financial shortages, budget overrun likely | Unachievable delivery date |
|  | 1 | Failure to meet the requirement would degrade system performance to a point where mission success is questionable |  | Failure results in operational delays and/or increased costs with expected value of $100K to $500k |  |
| CRITICAL | 2 | Some reduction in technical performance | Minor delays in software modifications | Some shortage of financial resources, possible overruns | Possible slippage in delivery date |
|  | 1 | Failure to meet the requirement would result in degradation of secondary mission |  | Costs, impacts, and/or recoverable schedule slips with expected value of $1K to $100K |  |
| MARGINAL | 2 | Minimal to small reduction in technical performance | Responsive software support | Sufficient financial resources | Realistic, achievable schedule |
|  | 1 | Failure to meet the requirement would create inconvenience or nonoperational impact |  | Error results in minor cost and/or schedule impact with expected value of less than $1K |  |
| NEGLIGIBLE | 2 | No reduction in technical performance | Easily supportable software | Possible budget underrun | Early achievable date |

Risk Projection:

- List all risks listed in column one.

- Categorizes risks by type:

- {business, project, etc.}

- Probability value (guess).

- Impact.

- Sort table based on impact and probability.

Risk Assessment:

- Define referent levels.

- {break even points - cost/schedule)

- Develop relationships between each reference factor.

- Determine region of termination, bounded by uncertainty curve.

- Try to predict compound combinations of risks - affecting referent level.

Risk Management (monitoring):

(No way to avoid risk)

- Determine causes of job turnover.

- Eliminate causes before project starts.

- After project starts, assume turnover is going to occur and ensure continuity.

- Make sure teams are organized and distribute information widely.

- Define documentation standards and be sure documents are produced in a timely manner.

- Conduct peer review of all work.

- Define backup staff.

Customer Questions

- Do you understand my needs?

- Can you design a system to meet my needs?

- How long will it take?

- How much will it cost?