CIS 375 SOFTWARE ENGINEERING

University Of Michigan-Dearborn

Dr. Bruce Maxim, Instructor

Project Schedule

(Break into phases)

- Deliverables:

- Documents.

- Demonstration of function.

- Demonstration of subsystem.

- Demonstration of accuracy.

- Demonstration of

- Milestones:

Completion of an activity of delivery (must be measurable).

Milestones must have definite a start and stop.

- Work breakdown structure:

Separate project development into phases, composed of steps (series of activities).

Digraph = activity graph.

Activities :

- Precursor.

- Duration.

- Due date.

- End point.

Critical path method:

- EST = earliest start time, EFT = earliest finish time.

- LST = latest start time, LFT = latest finish time.

- Slack = (LST - EST) or (LFT - EFT).

| Activity | Precursor | Duration | EST | EFT | LST | LFT | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Start | - | 0 | 0 | 0 | 0 | 0 | 0 |
| A | Start | 2 | 0 | 2 | 0 | 2 | 0 |
| B | Start | 3 | 0 | 3 | 4 | 7 | 4 |
| C | A | 5 | 2 | 7 | 2 | 7 | 0 |
| D | A,B | 4 | 3 | 7 | 7 | 11 | 4 |
| E | D | 2 | 7 | 9 | 11 | 13 | 4 |
| F | B,C | 6 | 7 | 13 | 7 | 13 | 0 |
| FINISH | E,F | 0 | 13 | 13 | 13 | 13 | 0 |

- EST(1) always = 0,  EFT(1) always = 0.

- LST(1) always = 0,  LFT(1) always = 0.

- EFT(I) = EST(I) + DUR(I).

- EST(I) = max(EFT of all predecessors).

- LFT(I) = LFT(I) - DUR(I).

- LFT(I) = min(LST of all predecessors).

- LFT(FINISH) = LST(FINISH) = EST(FINISH) = EFT(FINISH).

Critical Path is when all slack times = 0.

PERT:

(Program evaluation review technique)

|  |  |  |  |  | JAN |  |  |  | FEB |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TASK | EARLIEST START | LATEST START | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 17 | 24 |
| 1 | 1/1 | 2/5 | * | * | * | * | * | * |  |  |  |
| 2 | 1/1 | 1/8 | * | * |  |  |  |  |  |  |  |
| 3 | 1/9 | 1/22 | * | * | * | * |  |  |  |  |  |
| 4 | 1/9 | 1/22 | * | * | * | * |  |  |  |  |  |
| 5 | 1/23 | 2/1 |  |  |  | * | * | * |  |  |  |
| 6 | 1/23 | 2/1 |  |  |  | - | - | F |  |  |  |
| 7 | 1/23 | 2/17 |  |  |  | - | - | F | F | F |  |
| 8 | 2/2 | 2/17 |  |  |  |  |  | * | * | * | * |

- * = Critical activity.

- - = Non critical activity.

- F = Float or slack.

- Gant Charts:

- Overlay People On Gant Chart:

- Milestone Chart:

- Line Graph:

Pressman’s Project Plan:

- Project scope.

- Project schedule.

- Project team organization.

- Technical description of proposed system.

- Project standards, procedures, proposed methodologies.

- Quality assurance plan.

- Special tools & techniques.

- Configuration management plan.

- Documentation plan.

- Data management plan.

- Resource management plan.

- Test plan.

- Training plan.

- Security plan.

- Maintenance plan.