CIS 375 SOFTWARE ENGINEERING

University Of Michigan-Dearborn

Dr. Bruce Maxim, Instructor

Date: 9/22/97

Week 3

Dynamic Estimation Models:

- Putnam Model (initially based on 200 military models).

(Rayliegh curve -> skewed, median & mean offset from one another).

Based on:

- Volume of work.

- Difficulty gradient (complexity).

- Project technology factor.

- Time constraints, delivery.

E = y() = 0.3945 K;

{ represents optimal time} {K represents the area under the Rayliegh curve}.

D = K / 2;

{difficulty measure based on 2 and K}.

P = C2D-2/3;

{productivity measure}.

Ss = c K-1/5 4/3;

{ lines of code measure} {c represents the technology factor from survey}.

- Parr Model (variation of above):

Staff (t) = sech2 [(a t + c)/2].

- Jensen Model:

(less sensitive to compression)

Ss = Cte T K 1/2

- { Cte represents technology constraint with environmental adjustment}.

- COPMO (cooperative programming model):

- Size of project.

- Size of code.

E = E1 (S) + E2 (m);

{E represents total effort}.

{E1(S) represents the effort of one or people working independently

E1(S) = a + bs ,where a & b are empirically derived constants}.

{E2(m) represents the effort required to coordinate the development process

E2(m) = cm2 where m is the average number of team members}.

- It is not clear that all cost factors are incorporated in each model.

- Dynamic models have the ability to make adjustments to accommodate the fact that all cost factors are not considered.

Make-Buy-Decision:

- Is a computer-based necessary (cost effective?):

- If the company doesn’t know enough about procedures without computer, you can’t build a beneficial computer system for them.

- If things are only done once, it’s not worth designing a system.

- It must be a repeatable task & cost effective.

- Can an existing software package be purchased for the task?

- For example: if MS Access can be purchased for $150, why write a new one?  We cannot create a new one for this low cost.

Decision Steps:

- Develop specifications.

- Estimate internal cost & delivery.

- Select 3 or 4 candidate packages.

- Select reasonable components.

- Build a cost-benefit comparison matrix,								or Benchmarking (if from scratch you can’t do this).

- Evaluate each software package or component based on history with the product or vendor.

- Contact other users.

Now you’re in a good position to evaluate.

One way: build a decision tree.

Risks Analysis:

- Risk identification.

- Risk projection (impact of risks/likelihood of risk actually happening).

- Risk assessment (the change if it happens).

- Risk management.

Kinds Of Risk:

- Project risks:

- Schedule, budget, people, resources, etc.

- Technical risks:

- Design, implementation, interfacing, etc.

- Business risks:

- Building a project that the public actually wants.

Risk Projection (or estimation):

- Likelihood that a risk is real.

- Consequences of problem, if it occurs.

Risk Planner:

- Establish a scale indicating perceived likelihood.

- Determine consequences.

- Estimate impact on project (for each risk).

- Note overall accuracy of risk projection (to avoid misunderstanding).

Date: 9/24/97

Week 3

Sample Impact Assessment Table:

| CATEGORY \ COMPONENTS |  | PERFORMANCE | SUPPORT | COST | SCHEDULE |
| --- | --- | --- | --- | --- | --- |
|  | 1 | Failure to meet would result in mission failure |  | Failure results in increased costs and schedule delays with expected values in excess of $500K |  |
| CATASTROPHIC | 2 | Significant degradation to nonachievement of technical performance | Nonresponsive or unsupportable software | Significant, financial shortages, budget overrun likely | Unachievable delivery date |
|  | 1 | Failure to meet the requirement would degrade system performance to a point where mission success is questionable |  | Failure results in operational delays and/or increased costs with expected value of $100K to $500k |  |
| CRITICAL | 2 | Some reduction in technical performance | Minor delays in software modifications | Some shortage of financial resources, possible overruns | Possible slippage in delivery date |
|  | 1 | Failure to meet the requirement would result in degradation of secondary mission |  | Costs, impacts, and/or recoverable schedule slips with expected value of $1K to $100K |  |
| MARGINAL | 2 | Minimal to small reduction in technical performance | Responsive software support | Sufficient financial resources | Realistic, achievable schedule |
|  | 1 | Failure to meet the requirement would create inconvenience or nonoperational impact |  | Error results in minor cost and/or schedule impact with expected value of less than $1K |  |
| NEGLIGIBLE | 2 | No reduction in technical performance | Easily supportable software | Possible budget underrun | Early achievable date |

Risk Projection:

- List all risks listed in column one.

- Categorizes risks by type:

- {business, project, etc.}

- Probability value (guess).

- Impact.

- Sort table based on impact and probability.

Risk Assessment:

- Define referent levels.

- {break even points - cost/schedule)

- Develop relationships between each reference factor.

- Determine region of termination, bounded by uncertainty curve.

- Try to predict compound combinations of risks - affecting referent level.

Risk Management (monitoring):

(No way to avoid risk)

- Determine causes of job turnover.

- Eliminate causes before project starts.

- After project starts, assume turnover is going to occur and ensure continuity.

- Make sure teams are organized and distribute information widely.

- Define documentation standards and be sure documents are produced in a timely manner.

- Conduct peer review of all work.

- Define backup staff.

Customer Questions

- Do you understand my needs?

- Can you design a system to meet my needs?

- How long will it take?

- How much will it cost?

Project Schedule

(Break into phases)

- Deliverables:

- Documents.

- Demonstration of function.

- Demonstration of subsystem.

- Demonstration of accuracy.

- Demonstration of

- Milestones:

Completion of an activity of delivery (must be measurable).

Milestones must have definite a start and stop.

- Work breakdown structure:

Separate project development into phases, composed of steps (series of activities).

Digraph = activity graph.

Activities :

- Precursor.

- Duration.

- Due date.

- End point.

Critical path method:

- EST = earliest start time, EFT = earliest finish time.

- LST = latest start time, LFT = latest finish time.

- Slack = (LST - EST) or (LFT - EFT).

| Activity | Precursor | Duration | EST | EFT | LST | LFT | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Start | - | 0 | 0 | 0 | 0 | 0 | 0 |
| A | Start | 2 | 0 | 2 | 0 | 2 | 0 |
| B | Start | 3 | 0 | 3 | 4 | 7 | 4 |
| C | A | 5 | 2 | 7 | 2 | 7 | 0 |
| D | A,B | 4 | 3 | 7 | 7 | 11 | 4 |
| E | D | 2 | 7 | 9 | 11 | 13 | 4 |
| F | B,C | 6 | 7 | 13 | 7 | 13 | 0 |
| FINISH | E,F | 0 | 13 | 13 | 13 | 13 | 0 |

- EST(1) always = 0,  EFT(1) always = 0.

- LST(1) always = 0,  LFT(1) always = 0.

- EFT(I) = EST(I) + DUR(I).

- EST(I) = max(EFT of all predecessors).

- LFT(I) = LFT(I) - DUR(I).

- LFT(I) = min(LST of all predecessors).

- LFT(FINISH) = LST(FINISH) = EST(FINISH) = EFT(FINISH).

Critical Path is when all slack times = 0.

PERT:

(Program evaluation review technique)

|  |  |  |  |  | JAN |  |  |  | FEB |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TASK | EARLIEST START | LATEST START | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 17 | 24 |
| 1 | 1/1 | 2/5 | * | * | * | * | * | * |  |  |  |
| 2 | 1/1 | 1/8 | * | * |  |  |  |  |  |  |  |
| 3 | 1/9 | 1/22 | * | * | * | * |  |  |  |  |  |
| 4 | 1/9 | 1/22 | * | * | * | * |  |  |  |  |  |
| 5 | 1/23 | 2/1 |  |  |  | * | * | * |  |  |  |
| 6 | 1/23 | 2/1 |  |  |  | - | - | F |  |  |  |
| 7 | 1/23 | 2/17 |  |  |  | - | - | F | F | F |  |
| 8 | 2/2 | 2/17 |  |  |  |  |  | * | * | * | * |

- * = Critical activity.

- - = Non critical activity.

- F = Float or slack.

- Gant Charts:

- Overlay People On Gant Chart:

- Milestone Chart:

- Line Graph:

Pressman’s Project Plan:

- Project scope.

- Project schedule.

- Project team organization.

- Technical description of proposed system.

- Project standards, procedures, proposed methodologies.

- Quality assurance plan.

- Special tools & techniques.

- Configuration management plan.

- Documentation plan.

- Data management plan.

- Resource management plan.

- Test plan.

- Training plan.

- Security plan.

- Maintenance plan.