CIS 375

Lecture Notes

September 8, 1997

software engineering

- structured methodology

- Object Oriented Analysis / Object Oriented Design

- user interface design

costly software errors

- lost Voyager spacecraft

- radiation machine

- shot “commercial aircraft”

- 3 mile Island

- GRAPHS

- software vs. hardware as % of budget

- cost to correct software errors

software designers

- not invented here syndrome

- 80 % of all errors can be discovered by peer review

software characteristics

- software is developed or engineered - NOT manufactured

- software doesn’t wear out

- hardware failure

- GRAPH, p. 11 (fig. 1.2)

- software failure

- GRAPHS, p. 11, 12 (fig. 1.3, 1.4)

- most software custom built

- not assembled out of components

software engineering definition

- strategy for producing high quality software

high quality software?

- useful (to customer)

- portable

- maintainable

- reliable

- has integrity

- correct results w/ high degree of accuracy

- efficient

- consistency of function

- accessible (to user)

- good human engineering

- easy to learn

- easy to use

software development (models)

- systems approach

- distinguish between activities and objects

- determine object relationships

- system

- set of entities

- set of activities

- description of entity relationships

- boundary of system

- advantages of systems approach

- bounded system - problem identification is easy

- useful to think system = subsystem for purposes of extension

- GRAPH (system as subsystem)

- engineering approach

- art of producing systems involves the craft of programming

- fabricating software using off the shelf components

- why it doesn’t work

1.   customers not able to describe their needs completely or precisely

- customer changes specifications

software life cycle model

- requirements analysis and design

- system design

- program design

- program implementation

- unit testing

- integration testing

- system testing

- system delivery

- maintenance

waterfall model

- GRAPH (waterfall model graph)

- separate system function from design

CIS 375

Lecture Notes

September 10, 1997

software models

- waterfall model

- change = failure

- GRAPH (waterfall model)

- rapid prototyping model

- change is healthy

- GRAPH (rapid prototyping model)

- spiral model

- GRAPH (spiral model - pp. 40, 41 - fig. 2.8, 2.9)

- fourth generation techniques

- non-procedural DB query language

- report generator

- data manipulation tool

- high level graphics capability

- GRAPH (4GL techniques)

capability maturity model (CCM)

- strategy for improving software process

- level 1 - initial process

- ad hoc approach to software design

- inputs ill defined

- outputs expected (transitions not defined or uncontrollable)

- level 2 - repeatable process

- requirements are input

- code output

- constraints (budget & time)

- metrics (project related)

- software size

- personnel effort

- requirement volatility

- employee turnover

- level 3 - defined processes

- activities of process have clearly defined entry & exit conditions

- intermediate products well-defines and easily visible

- metrics

- requirements complexity

- code complexity

- test complexity

- failures discovered

- code defects discovered

- product defect density

- pages of documentation

- level 4 - managed processes

- information from early process activities can be used to schedule later process activities

- metrics

- process type

- producer reuse

- consumer reuse

- defect identification mechanism

- defect density model for testing

- configuration management scheme

- module completion rates over time

- level 5 - optimizing processes

- measures from activities are used to improve processes

- using metrics

- assess process level

- determine metrics to use

- recommend metrics, tools, techniques

- estimate project costs & schedule

- collect metrics at appropriate level

- construct project database

- evaluate cost & schedule

- evaluate productivity & quality

- form basis for future estimates

benefits: process maturity & metrics

- enhanced understanding of process

- increased control over process

- clear migration path to more mature process

- more accurate estimates of cost & schedule

- more objective evaluation of changes (technology, tools, methods)

- more accurate estimation of changes on project cost & schedule

project management

- people

- customer

- managers

- software engineers

- users

- problem

- scope

- context

- information

- function

- performance

- decomposition

- process

- engineering paradigm

- 90 / 10 rule

- software development team

- configuration management team

- maintenance team

- librarian

- GRAPH (software life cycle - team member placement)

problems with software development

- changing constraints & requirements

- phased system development

- development system

- production system

- interactions with other systems

- nature of computer system itself

- digital vs. analog vs. hybrid

- logic of software development

- type of software projects

CIS 375

Lecture Notes

September 15, 1997

software development team

- people = personnel

- GRAPH (people vs. productivity)

- CHART (intuitive vs. rational vs. introvert vs. extrovert)

- project team organization

- hierarchical

- ORG CHART (w/chief programmer)

- egoless

- CHART (pentagon)

- framework of activities

- customer communication

- planning

- risk analysis

- engineering

- construction & release

- customer evaluation

- CHART (fig. 3.2, p. 70)

cost estimation

- cost types

- facilities

- people

- project methods & tools

- cost models

- experiential

- static (similar to regression)

- dynamic

- experiential models

- expert judgment (guesses)

- A = pessimistic estimate

- B = most likely

- C = optimistic estimate



E	= 	(A + 4B + C) / 6

- Delphi technique

- group of experts make “secret” guesses

- compute group average & present it to group

- wolverton model

{old, new} * {easy, moderate, hard}

software type matrix

type:		OE	OM	OH	NE	NM	NH

control		21	27	30	33	40	45

I/O

pre/post

processes

.

.

.

time control	75	75	75	75	75	75

- estimate models (in terms of cost)

C(k) = S(k) * Ci,j (k)

system =  (k = 1..n) C(k)

- function points (fig. 4.5, p.86)

FP = T * (0.65 + 0.01 * Q)

- questions (fig. 4.1, p. 87)

- problems with expert judgment

- subjective (consensus tough)

- extrapolating project to project is difficult

- adding people doesn’t always increase productivity

- users & project managers tend not to estimate costs well

- cost matrices require periodic updates

regression & correlation

X				Y

(independent)			(dependent measure)

- mean	

x = xi / N

- variance	2

(xi2 / N) - x2

- covariance	 * y

(xiyi / N) - xy

- y = mx + b

- correlation = r				GRAPH (y = mx + b)

CIS 375

Lecture Notes

September 17, 1997

regression

y = mx + b

x		y		x2		x * y		y2

1		1		1		1		1

3		2		9		6		4

4		4		16		16		16

N = 8		6		4		36		24		16

8		5		64		40		25

9		7		81		63		49

11		8		121		88		64

14		9		196		126		81

x = 56		y = 40	 	x2 = 524	 xy = 364	 y2 = 256

x = x / N = 56 / 8 = 7

y = y / N = 40 / 8 = 5

x2 = ( x2 / N) - (x )2 = (524 / 8) - (7)2 = 65.5 - 49 = 16.5

x = (16.5) = 4.062

y2 = ( y2 / N) - (y)2 = (256 / 8) - (5)2 = 7

y = (7) = 2.6458

xy = ( xy / N) - (x)(y) = (364 / 8) - (7)(5) = 45.5 - 35 = 10.5

m = xy /  x2 = 10.5 / 16.5 = .6364

b =y - (m * x)= 5 - .6364(7) = .5452

y = .6364x + .5452

r = xy / (xy) = 10.5 / (4.062)(2.6458) = .9770

r2 = (.9770)2 = .9545

EXAMPLE GRAPHS (different R values: 1.0, .82, .55, 0.0, -1.0)

regression models

- linear model

E = C0 +  cixi	(E = effort - person months, ci = regression coefficients)

- Nelson

N = 169 projects

104 possible cost factors

14 - identifies

- static non-linear model

E = C0 +  (i = 1..n) cixidi

- size of code

E = (a + bS2) m(x)	(m = multiplier)

- Halstead’s Software Science

assumptions:

- complete algorithm description exists

- programmer - working alone knows what he/she is doing

based on:

n = # operators & operands in module

N = total # operators & operands

- N = Kss

- (K = average # operators & operands per lines of code, s = size estimate lines of code)

- N = n log2(n/2)

- effort	E = (N2 log2(n)) / 4

- Watson-Felix model

- E = 5.25S0.91		(S = lines of code)

- P =  (i = 1..29) wixi	(wi = 1 (increases), 0, -1 (decreases))

- Bailey & Basili

- ^E = 5.5 + 0.73S1.6	(^E = predicted effort)

- R = E / ^E = actual effort / predicted effort

- effort adjust

ERadj	= R - 1 if R ≥ 1

= 1 - (1/R) if R < 1

Eadj	= (1 + ERadj)E if R ≥ 1

= E / (1 + ERadj) if R < 1

ERadj	= a * METHOD + b * COMPLEXITY

+ c * EXPERIENCE + d

4.	COCOMO (COnstructed COst MOdel)

- levels

- basic

- intermediate

- detailed

E = aSb m(x)	(S = code size (KLOC))

m(x) =  (i = 1..15) m(xi)

basic			intermediate

mode			a	b		a	b

organic			2.4	1.05		3.2	1.05

semi-detached		3.0	1.12		3.0	1.12

embedded		3.6	1.20		2.8	1.20

- questionnaire

- product attributes

RELY - reliability

DATA - size of DB

CPLX - complexity of system

- computer attributes

TIME - execution

STOR - storage

VIRT - virtual volatility

TURN - response time

- personnel

ACAP - analyst capability

AEXP - analyst experience

PCAP - programmer capability

MEXP - machine experience

LEXP - language experience

- project attributes

MODP - modern practices

TOOL - software tools

SCED - dev. schedule

- example

basic	(REMEMBER m(x) ALWAYS = 1)

organic

E = 2.4(KLOC)1.05 = 2.4(3)1.05 = 7.6065

CIS 375

Lecture Notes

September 22, 1997

regression models (cont.)

- COCOMO (cont.)

- E (person-months) = 2.4(KLOC)1.05 = 2.4(3)1.05 = 7.6065

- D (duration) = CEd = 2.5(7.6065)0.38 = 5.4049

dynamic models

- Putnam (Rayleigh)

- GRAPH (Rayleigh curve)

- volume of work

- difficulty gradient (complexity)

- project technology factor

- delivery time constraints

E = y(T)  optimal development time

= 0.3945K  area under Rayleigh curve

D (difficulty) = K/T2

P (productivity) = CiD-2/3

Ss (lines of code) = ck-1/3T4/3	(c  technology factor)

- Parr model

- staff (t) = sech2 [(at + c) / 2]

- GRAPH

- Jensen model (less sensitive to compression)

Ss = CeTk1/2		(e = tech constraint - w/ environmental adjustment)

- COPMO (COoperative Programming MOdel)

- size of project

- size of code

E = E1(S) + E2(m)

- E = total effort

- E1(S) = a + bS  lines of code

= effort 1 or more members working independently

- E2(m) = cmd

= effort required to coordinate development process

- m = avg. # team members

make-buy decision

- is a computer-based necessary?

- can existing software be purchased or modified for the task?

- decision steps (p. 125)

- develop specifications

- estimate internal costs & delivery

- a.	select 3 or 4 candidate packages

- select reusable components

- build comparison matrix OR benchmarking

- evaluate each software package or component based on history with product or vendor

- contact other users

- decision tree (p. 126)

- estimated build = (.3)$380K + (.7)$450K = $429,000

- estimated reuse = (.4)$275K + .6[(.2)$310K + (.8)$490K] = $382,000

risk analysis

- risk identification

- risk projection

- risk assessment

- risk management

kinds of risk

- project risks

- (schedule, budget, people, resources, etc.)

- technical risks

- (design, implementation, interfacing, etc.)

- business risks

- (building project - the public wants)

- projection (or estimation)

- likelihood that a risk is real

- understand consequences of problems if they occur

risk planner

- establish a scale indicating perceived likelihood

- determine consequences

- estimate impact on project

- estimate overall accuracy of risk projection (to avoid misunderstanding)

CIS 375

Lecture Notes

September 24, 1997

simple impact assessment

CHART (components vs. category)

risk projection (estimation)

- all risks listed in column 1

- categorize risks by type

- business, project, …

- probability value (guess)

- impact 1 to 4

- sort table based on impact & probability

risk table

| risks | category | probability | impact |
| --- | --- | --- | --- |
| - | BU | 60% | 1 |
| - | PR | 30% | 2 |
| - |  |  | 3 |
| - |  |  | 4 |

risk assessment

GRAPH (projected cost overrun vs. project schedule)

- define referent levels (break even points - cost, schedule)

- develop relationship between referent factor

- determine region of termination bounded by uncertainty curve

- try to predict compound combinations of risks - affecting referent level

risk management (monitoring)

- determine causes of job turnover

- eliminate cause before project starts

- after project starts - assume turnover will occur - try to ensure continuity

- make sure teams are used & distribute information widely

- define documentation standards & be sure documents are produced in timely manner

- conduct peer review of all work

- define backup draft

- customer questions

- do you understand my needs?

- can you design a system to meet my needs?

- how long will it take?

- how much will it cost?

project schedule (break into phases)

- deliverables

- documents

- demonstration of function

- demonstration of subsystems

- demonstration of accuracy

- demonstration of reliability, speed of security

- define milestones

- completion of activity <definite start & finish> of deliverable [must be measurable]

- work break down structure

- separate project development into phases composed of steps (series of activities

critical path method (CPM)

GRAPH (digraph)

| activity | pred. | duration | EST | EFT | LST | LFT | slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| START | - | 0 | 0 | 0 | 0 | 0 | 0 |
| A | START | 2 | 0 | 2 | 0 | 2 | 0 |
| B | START | 3 | 0 | 3 | 4 | 7 | 4 |
| C | A | 5 | 2 | 7 | 2 | 7 | 0 |
| D | A,B | 4 | 3 | 7 | 7 | 11 | 4 |
| E | D | 2 | 7 | 9 | 11 | 13 | 4 |
| F | B,C | 6 | 7 | 13 | 7 | 13 | 0 |
| FINISH | E,F | 0 | 13 | 13 | 13 | 13 | 0 |

EST(1) = 0	EFT(1) = 0	LST(1) = 0	LFT(1) = 0

EFT(I) = EST(I) + DUR(I)

EST(I) = max.(EFT all predecessors)

LFT(FINISH) = LST(FINISH) = EST(FINISH) = EFT(FINISH)

LST(I) = LFT(I) - DUR(I)

LFT(I) = min.(LST all successors)

slack time = LST - EST = LFT - EFT

PERT (Program Evaluation & Review Technique)

|  | Early | Late | January |  |  |  |  | February |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| task | Start | Start | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 17 | 24 |
| 1 | 1/1 | 2/5 | * | * | * | * | * | * |  |  |  |
| 2 | 1/1 | 1/8 | * | * |  |  |  |  |  |  |  |
| 3 | 1/9 | 1/22 | * | * | * | * |  |  |  |  |  |
| 4 | 1/9 | 1/22 | * | * | * | * |  |  |  |  |  |
| 5 | 1/23 | 2/1 |  |  |  | * | * | * |  |  |  |
| 6 | 1/23 | 2/1 |  |  |  | - | - | F | F |  |  |
| 7 | 1/23 | 2/17 |  |  |  | - | - | F | F |  |  |
| 8 | 2/2 | 2/17 |  |  |  |  |  | * | * | * |  |
| * = critical |  |  |  |  |  |  |  |  |  |  |  |
| - = non-critical |  |  |  |  |  |  |  |  |  |  |  |
| F = float or slack |  |  |  |  |  |  |  |  |  |  |  |

- Gantt chart

- CHART (example Gantt chart)

- overlay people on Gantt chart

- CHART (example - people on Gantt chart)

- milestone chart (grief / joy)

- CHART (example milestone chart)

- line graph

- GRAPH (example line graph)

project plan

- project scope

- project schedule

- project team organization

- technical description of proposed system

- project standards, procedures, proposed methodologies

- quality assurance plan

- special development tools & techniques

- configuration management plan

- documentation plan

- data management plan

- resource management plan

- test plan

- training plan

- security plan

- maintenance plan